## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | Tuesday | Wednesday | Thursday | Friday | Monday | SPRINT REVIEW
Review Current Sprint
Review our work |  | Shawn, Carl, Anna | DONE | 15 MIN | 15 | 15 | 10 | 0 | 10 | 50 MIN
Find out what we have done |  | Shawn, Carl, Anna | DONE | 15 MIN | 15 | 15 | 5 | 0 | 0 | 35 MIN
Determine new changes with Client
Review Client feedback |  | Shawn, Carl, Anna | DONE | 30 MIN | 10 | 0 | 15 | 0 | 5 | 30 MIN
Figure out what needs to be changed |  | Shawn, Carl, Anna | DONE | 15 MIN | 25 | 0 | 10 | 0 | 10 | 45 MIN
Edit and Amend code
Rework code |  | Shawn, Carl, Anna | DONE | 15 MIN | 0 | 15 | 25 | 0 | 15 | 55 MIN
Rework deliverables |  | Shawn, Carl, Anna | DONE | 45 MIN | 0 | 0 | 20 | 0 | 30 | 50 MIN
Determine changes |  | Shawn, Carl, Anna | DONE | 20 MIN | 30 | 0 | 5 | 0 | 5 | 40 MIN
Update UML |  |  | DONE | 10 MIN | 0 | 0 | 15 | 0 | 10 | 35 MIN
Table Check Deliverables
Make sure changes are viable |  | Shawn, Carl, Anna | DONE | 15 MIN | 0 | 0 | 5 | 0 | 15 | 30 MIN
Make sure everything is done |  | Shawn, Carl, Anna | DONE | 25 MIN | 0 | 0 | 5 | 0 | 25 | 30 MIN
Finalize and Push Additions
Push to repo |  | Shawn, Carl, Anna | DONE | 5 MIN | 0 | 0 | 0 | 0 | 5 | 5
Compare old and new project |  | Shawn, Carl, Anna | DONE | 10 MIN | 0 | 0 | 0 | 0 | 5 | 5
Determine with client if acceptable |  | Shawn, Carl, Anna | DONE | 10 MIN | 0 | 0 | 0 | 0 | 10 | 10
TOTAL |  |  |  | 3H 35 MIN | 95 | 45 | 115 | 0 | 145 | 6 HOURS 35 MIN