## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | 4/10 - 4/15 | 4/17 - 4/21 | 4/24 - 4/28 | 2023-04-29 | 2023-04-30 | SPRINT REVIEW
Prepare Project for new deliverables |  |  |  | 1 Hour
Determine new Changes |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 1/4 Hour | 0 | 0 | 0 | 0
Figure out basic Implementation |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 1/4 Hour | 0 | 0 | 0 | 0
Determine new Additions |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 1/4 Hour | 0 | 0 | 0 | 0
Figure out Expectations of Client |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 1/4 Hour | 0 | 0 | 0
Develop our Code |  |  |  | 2 Hours 45
Begin basic implementation |  | Shawn, Carl, Anna | DONE | 3/4 Hour | 0 | 1/4 Hour | 1 Hour | 2 Hours | 0
Make old code compatable |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 1/4 Hour | 0 | 1/4 Hour | 0
Redesign as needed |  | Shawn, Carl, Anna | DONE | 2/4 Hour | 0 | 0 | 1/4 Hour | 1/4 Hour | 0
Make changes uniform |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 1/4 Hour | 1/4 Hour | 0
Make Changes to UML |  |  |  | 1 Hour 15
Figure out what needs to change |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 1/4 Hour | 0 | 1/4 Hour | 0
Add appropriate classes |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 1/4 Hour | 0
Redraw as needed |  | Shawn, Carl, Anna | DONE | 2/4 Hour | 0 | 0 | 0 | 1/4 Hour | 0
Give a final look over to the chart |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 1/4 Hour | 0
Refactoring |  |  |  | 2 Hours 30
Review our groups code |  | Shawn, Carl, Anna | DONE | 2/4 Hour | 0 | 0 | 0 | 2/4 Hour | 0
Make sure all of our code is compatable |  | Shawn, Carl, Anna | DONE | 2/4 Hour | 0 | 0 | 0 | 1/4 Hour | 0
Optimize |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 1/4 Hour | 0
Finish final adjustments |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 1/4 Hour | 0
Desk Checking |  |  |  | 1 Hour
Review client expectation |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 0 | 1/4 Hour
Make sure expectations are met |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 0 | 1/4 Hour
Make final updates to deliverables |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 0 | 1/4 Hour
Push to git and check for erros |  | Shawn, Carl, Anna | DONE | 1/4 Hour | 0 | 0 | 0 | 0 | 1/4 Hour
TOTAL |  |  | FINISHED | 7 Hours 30 | 3/4 Hour | 1 Hour | 1 Hour 30 | 5 Hours | 1 Hour | 9 Hours 15