## Agile Sprint Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
[5 empty] | Tursday | Thursday | Tuesday | Thursday | Tuesday | Thursday
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3 | 5
Task |  |  |  | 8 | 6 | 0 | 0 | 0 |  | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 78 | 60 | 59 | 41 | 20 | 25 | 18 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Junit Testing For Program
Junit testing |  | Shawn | Not done | 1 Hour
Junit testing |  | Anna | Not done | 1 Hour
Junit testing |  | Carl | Not done | 1 Hour
User Strategy
Define our objective |  | Shawn, Carl, Anna | Not done | 30 Minutes
Figure out implementation |  | Shawn, Carl, Anna | Not done | 30 Minutes
Program and write our design |  | Shawn, Carl, Anna | Not done | 3 Hours
Final Debugging |  | Shawn, Carl, Anna | Not done | 1 Hour
UML Update
Determine new UML layout |  | Shawn, Carl, Anna | Not done | 30 Minutes
Redesign UML |  | Shawn, Carl, Anna | Not done | 1 Hour
Documentation
Ensuring understanding of Code |  | Shawn, Carl, Anna | Not done | 1 Hour
Figuring out what needs to be changed |  | Shawn, Carl, Anna | Not done | 30 Minutes
Adding/replacing documentation |  | Shawn, Carl, Anna | Not done | 1 Hour
Final Check
Read over everything, make final changes |  | Shawn, Carl, Anna | Not done | 30 Minutes
TOTAL |  |  |  | 12.5 Hours combined | 0 | 0 | 0 | 0 | 0 | 0